## Sheet1
W/O No | Description | Duration | Asset No | Trades | Due Start | Work Order Status Description | Raised | Start Date | Priority | Job Type | Department | Materials Cost | Labour Cost | Other Cost | Asset Description
6001 | MF420 Madmax Pump Engine Replacement | 36 | NBG-PP-35 | HV/Pump 36 Hrs | 2025-05-22 00:02 | Scheduled | 2025-04-23 14:49 | 2025-05-06 12:00 | Current Planning Period | Capital | Mine Operations | 0 | 16190.64 | 0 | MF420EX PUMP (Booster)
6803 | Trucks - Truck 411 Volvo Spout Truck Weekly Inspection / Service Nightshift Please | 3 | NBG-TRK-411 | HV/LV Tec 3 Hrs | 2025-05-19 00:02 | Scheduled | 2025-05-05 11:46 |  | Current Planning Period | PM | Mine Maintenance | 0 | 283.56 | 0 | VOLVO Spout Truck
6805 | Trucks - Truck 411 Volvo Spout Truck Weekly Inspection / Service Nightshift Please | 3 | NBG-TRK-411 MODULE | HV/LV Tec 3 Hrs | 2025-05-19 00:02 | Scheduled | 2025-05-05 11:46 |  | Current Planning Period | PM | Mine Maintenance | 0 | 283.56 | 0 | VOLVO Spout Truck - MODULE
6774 | Trucks - Isuzu including Emergency Services Fire Monthly Inspection / Service - D | 3 | NBG-TRK-402 | Fitter co 3 Hrs Kailen Lysaght (3.00 Hrs Completed) | 2025-05-18 07:32 | Closed | 2025-05-05 11:45 | 2025-05-18 07:32 | Current Planning Period | PM |  | 0 | 0 | 0 | ISUZU DUAL CAB, 7 SEATER
3234 | Leaks from power pack directional solenoid valve block - D | 8 | NBG-PP-38TE | HV/Pump 8 Hrs Rhys Height (8.00 Hrs Completed) | 2025-05-18 00:02 | Closed | 2025-02-07 10:58 |  | Next Planning Period | Correct | Mine Operations | 0 | 884.24 | 0 | TRACK FRAME DRIVE ENGINE
5172 | Replace rain caps - on staging shelf. - D Use Work Platform | 3 | NBG-PP-38 | HV/LV Tec 3 Hrs (3.00 Hrs Completed) | 2025-05-18 00:02 | Closed | 2025-04-02 17:17 |  | Current Planning Period | Correct | Mine Operations | 357.09 | 283.56 | 0 | Track MF420EX PUMP (Suction)
6169 | Pit Pump / Dewatering Fitter Daily Hours Allocation | 10 | Dewatering | HV/Pump 10 Hrs Rhys Height (3.00 Hrs Completed) | 2025-05-17 22:02 | Closed | 2025-04-29 06:13 |  | Current Planning Period | Correct | Mine Operations | 0 | 1105.3 | 0 | Dewatering