## Sheet1
Printed | W/O No | Asset No | Description | Asset Description | Status | Due Start | Due Finish | Job Type | Reference No | Priority | Raised | Start Date | Finished Date | Duration | Account Code | Department | Parent Asset | Material Costs | Other Costs | Policy Number | Group Number | Document Count | Permits Outstanding | Risk Type | Hazard Description | Risk Score | Risk Rating
FALSE | 8095 | NBG-BUS-454. | Please check ready for licensing •Lights – all internal and external must be working •Seatbelts – all to be in working order, no fraying or damaged straps •Tyres – must have correct tyre pressure and relevant tread •Windscreens – to be free ... | 1GVD 202 - 12 Seater Commuter Bus | Ready for Scheduling |  |  | Inspection |  | Next Planning Period | 2025-06-12 17:49 |  |  | 0 | Newmont | Mine Maintenance | Hauling/Anc | 0 | 0 |  |  | 0 | 0
FALSE | 7873 | NBG-TRL-049a | Trailer three monthly inspections - this can be split into just trailers and trailers and gensets later. N Asset in use, can't access it | Trailer Evac | Ready for Scheduling | 2025-06-17 02:03 |  | Not Done |  | Next Planning Period | 2025-06-10 13:50 |  |  | 2 | Newmont | Mine Maintenance | Shovels | 0 | 0 | 245 |  | 1 | 0
FALSE | 7402 | NBG-LV-328 | Light Vehicle Inspection LC- 1 Monthly N/S Nightshift No show | 003649 - Landcruiser - Wagon | Ready for Scheduling | 2025-06-16 02:03 |  | Not Done |  | Next Planning Period | 2025-05-27 14:04 |  |  | 3.5 | Newmont | Mine Operations | Planning | 47.34 | 0 | 59 |  | 2 | 0
FALSE | 7037 | NBG-LV-155 | Light Vehicle Inspection LC - 2 Monthly D/S Dayshift | 1CKX 540 - LandCruiser - Ambulance | Ready for Scheduling | 2025-05-28 04:03 |  | Not Done |  | Next Planning Period | 2025-05-19 11:03 |  |  | 3.5 | Newmont | Admin Support | Medical | 53.64 | 0 | 112 |  | 2 | 0
FALSE | 6935 | NBG-BUS-462. | Remove and replace steering wheel, and glove box | 1GVD 201 - 12 Seater Commuter Bus | Ready for Scheduling |  |  | Damage |  | Next Planning Period | 2025-05-13 06:56 |  |  | 0 | Newmont | Mine Maintenance | Hauling/Anc | 2440.96 | 0 |  |  | 0 | 0
FALSE | 6861 | NBG-LV-207. | Replace Mesh grill | 1HHT 928 - Hilux - Dual Cab - Tray Back | Ready for Scheduling | 2025-05-30 22:03 |  | Not Found |  | Next Planning Period | 2025-05-07 16:51 |  |  | 0 | Newmont | Process Maintenance | Electrical | 40.8 | 0 |  |  | 0 | 0
FALSE | 5753 | NBG-LV-321 | Ready vehicle for site use, Green sticker wheel chock holders | 019470 - Landcruiser - Single Cab - Tray Back | Ready for Scheduling |  |  | Correct |  | Within 24 Hours | 2025-04-16 17:35 |  |  | 0 | Newmont |  | Mine Services | 0 | 0 |  |  | 0 | 0
FALSE | 4786 | Koormal Workshop | HSR Safety Inspection (5 Weekly Inspection) | Koormal Workshop Boddington Gold Mine | Ready for Scheduling |  |  | Inspection |  | Next Planning Period | 2025-03-24 17:10 |  |  | 1 |  | Mine Maintenance | Mine Maintenance | 0 | 0 | 53 |  | 1 | 0
[18 empty] | Sum = $2,582.74 | Sum = $0.00